## AHI-Sprint Backlog
Sprint Backlog for Project: AHI App Development
Story ID | Resource | Story/Task | Time Required | Time Remaining
1 |  | User Story: To track current market trends in the skincare industry and monitor customer interest in real-time. | 60
|  | Task 1: Set up real-time analytics for customer views and preferences. | 10
|  | Task 2: Develop competitive analysis data generation system using worldwide sales data. | 20
|  | Task 3: Implement sales and trend tracking features. | 10
|  | Task 4: Test and validate the real-time analytics and trend tracking features. | 12
|  | Task 5: Deploy the new analytics and tracking system to production. | 8
2 |  | User Story: To ensure secure order invoicing and real-time reporting on inventory and product availability. | 56
|  | Task 1: Develop a secure platform for invoicing and order processing. | 10
|  | Task 2: Integrate real-time financial sales and forecasting metrics. | 15
|  | Task 3: Implement inventory management with real-time availability updates. | 13
|  | Task 4: Test the secure invoicing platform and real-time metrics integration. | 12
|  | Task 5: Deploy and monitor the invoicing and reporting system. | 6
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5