## AHI-Comm Mgt Plan
Communications plan for project: AHI App Development
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Project Kick-off Meeting | Cary Manning | All project stakeholders | April 1, 20XX | In-person and video conference | Introduce the project, goals, timelines, and key responsibilities.
Weekly Status Updates | Cary Manning | Project Team, Mary Smithers | Every Monday | Email, Project Management Tool | Provide updates on project progress, address any issues, and align on priorities.
Design Phase Review | Keiko Tanaka | Development and IT Teams | May 31, 20XX | In-person meeting | Review design phase outcomes, gather feedback, and approve the design for the next phase.
Risk Management Workshop | Cary Manning | Project Team, Mary Smithers | Monthly (first Friday) | In-person or virtual workshop | Identify and assess new risks, update the risk register, and discuss mitigation strategies.
User Acceptance Testing (UAT) Briefing | Priya Service | Marketing Team, IT Team | September 15, 20XX | Email and video conference | Prepare teams for UAT, discuss the testing plan, and define success criteria.
Change Control Board (CCB) Meeting | Cary Manning | CCB Members | Bi-weekly | In-person or virtual meeting | Review and approve or reject any changes to the project scope, schedule, or budget.
Project Closure Report | Cary Manning | All project stakeholders | November 30, 20XX | Email, Project Management Tool | Summarize project outcomes, lessons learned, and final performance against goals
Version: 01 |  |  | Date: 15/08/2024