## AHI-Quality Mgt Plan
Quality management plan for project: AHI App Development
Part I: Project objectives
1. Develop an app to provide real-time analytics and marketing data.
2. Streamline marketing processes by automating data collection and analysis.
3. Ensure a 20% ROI in the first year through improved marketing efficiency.
4. Improve employee engagement by providing effective tools and processes for analyzing market trends and customer data.
5. Improve insights into customer demographics and preferences for better product offerings.
6. Complete the project on schedule and within the $250,000 budget.
7. Ensure that the app is developed and launched on schedule, particularly the launch by October 1, 20XX, to maintain market competitiveness.
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Cary Manning | Project Manager |  | x | x | x
Keiko Tanaka | Quality Assurance Lead | x |  | x | x
Pat Johnson | Quality Control Lead | x |  | x | x
Priya Service | IT Subject Matter Expert | x |  | x
Ram Samuels | Marketing Subject Matter Expert | x |  | x
External Vendor | Development Team | x
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Audit Requirements Compliance |  |  | Verify Code Integrity
Audit Process Compliance |  |  | Verify Functional Completeness
Audit Vendor Performance |  |  | Verify User Acceptance