## AHI-Risk Register
Project: AHI App Development Date: 15/08/2024
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Integration issues with existing systems | App fails to integrate properly with legacy systems | Increased development time and cost | Cary Manning | T | 3 | 4 | 12 | Integration testing failures | Conduct thorough integration testing and validation
2 | Reduced marketing effectiveness and ROI | Marketing team’s requirements are not met | Reduced marketing effectiveness and ROI | Cary Manning | T | 3 | 4 | 12 | Discrepancies in requirements | Regular cross-team meetings and requirement reviews
3 | Inadequate user feedback during development | App does not meet user expectations | Lower user satisfaction and adoption | Priya Service | T | 4 | 3 | 12 | Negative user feedback | Implement iterative feedback sessions and adjustments
4 | High turnover rate in the development team | Project knowledge loss and delays | Increased project risk and delays | Cary Manning | T | 3 | 4 | 12 | High employee turnover | Develop knowledge transfer and retention strategies
5 | Budget overruns due to unforeseen expenses | Project exceeds the $250,000 budget | Financial strain and project scaling back | Cary Manning | T | 4 | 4 | 16 | Cost overruns identified | Implement strict budget monitoring and control measures
6 | Security vulnerabilities in the app | Data breach or security issues | Loss of customer trust and legal repercussions | Keiko Tanaka | T | 3 | 5 | 15 | Security breaches during testing | Conduct regular security audits and incorporate best practices
7 | Partnership with tech innovators | Collaborate with tech innovators for advanced features | Enhanced app functionality and marketability | Cary Manning | O | -2 | 5 | -10 | Opportunities for tech partnerships | Seek and leverage partnerships for innovative features
Total Risk Score | [7 empty] | 69 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low