## Template
High-Level Budget: Resource Breakdown Structure Project Name: AHI APP Development Date: 15/08/2024
WBS identifier # | Work package | Internal personal required | External personnel required | Venue costs | Materials required | Supplies required | Equipment required | Comments | Total direct costs
1.1 | Design Phase | 5 | 2 | 0 | 3000 | 1000 | 5000 | Design and planning phase including vendor selection and approval | 9000
1.1.1 | Gain final design approval | 1 | 0 | 0 | 500 | 100 | 500 | Internal review and approval | 1100
1.1.2 | Identify vendor to design and develop app | 1 | 1 | 0 | 500 | 200 | 500 | Vendor selection process | 1200
1.1.3 | Solicit initial design feedback | 1 | 0 | 0 | 200 | 100 | 200 | Initial feedback round | 500
1.1.4 | Define key app functionality requirements | 1 | 1 | 0 | 300 | 200 | 300 | Requirements gathering | 800
1.1.5 | Develop initial design | 2 | 0 | 0 | 500 | 200 | 1000 | Initial design development | 1700
1.1.6 | Finalize vendor contract | 1 | 1 | 0 | 300 | 100 | 500 | Contract finalization with vendor | 900
1.1.7 | Update design based on feedback | 2 | 0 | 0 | 200 | 100 | 500 | Design update after feedback | 800
2.1 | Development Phase (90 days) | 10 | 4 | 0 | 10000 | 2000 | 15000 | Development of app including beta testing and updates | 27000
2.1.1 | Develop initial prototype | 3 | 1 | 0 | 3000 | 500 | 5000 | Initial prototype development | 8500
2.1.2 | Perform prototype beta test | 2 | 1 | 0 | 1500 | 500 | 2000 | Beta testing of prototype | 6000
2.1.3 | Solicit best test feedback | 1 | 1 | 0 | 1000 | 300 | 1000 | Gathering feedback post beta testing | 3300
2.1.4 | Update prototype based on feedback | 2 | 0 | 0 | 2000 | 500 | 3000 | Updating the prototype based on gathered feedback | 5500
2.1.5 | Implement IT upgrades | 2 | 1 | 0 | 15000 | 300 | 3000 | IT infrastructure upgrades | 5800
2.1.6 | Develop an app launch plan | 2 | 0 | 0 | 1500 | 400 | 2000 | Planning for the app launch | 3900
2.1.7 | Gain prototype sign-off | 1 | 0 | 0 | 500 | 100 | 1000 | Final approval and sign-off on prototype | 1600
3.1 | Test Phase (30 days) | 3 | 1 | 0 | 4000 | 1000 | 5000 | Comprehensive testing of the final app prototype | 10000
3.1.1 | Test the final app prototype | 2 | 0 | 0 | 1500 | 300 | 2000 | Final app prototype testing | 3800
3.1.2 | Begin full-scale development | 3 | 1 | 0 | 2000 | 500 | 3000 | Transition to full-scale development | 8500
3.1.3 | Begin IT hiring | 1 | 1 | 0 | 500 | 200 | 1000 | Hiring IT personnel | 1700
3.1.4 | Gain customer acceptance | 2 | 0 | 0 | 1000 | 300 | 2000 | Customer acceptance of final product | 3300
3.1.5 | Approve the launch plan | 1 | 1 | 0 | 500 | 200 | 1000 | Approval of the app launch plan | 1700
3.1.6 | Train marketing personnel on new app | 2 | 0 | 0 | 500 | 300 | 1000 | Training sessions for marketing teams | 1800
4.1 | Launch and Improvement Phase (60 days) | 7 | 3 | 0 | 10000 | 2000 | 20000 | Launch and monitoring of the new app, along with planning v2 | 9000
4.1.1 | Launch the new app | 3 | 1 | 0 | 3000 | 1000 | 5000 | Initial app launch | 5500
4.1.2 | Monitor app performance | 2 | 0 | 0 | 2000 | 500 | 3000 | Ongoing performance monitoring | 8500
4.1.3 | Plan v2 upgrades | 3 | 1 | 0 | 1500 | 500 | 2000 | Planning for version 2 upgrades | 1700
4.1.4 | Finalize new hires | 1 | 1 | 0 | 500 | 200 | 1000 | Completion of new hiring | 5500
4.1.5 | Implement app upgrades | 2 | 0 | 0 | 200 | 500 | 3000 | Upgrades implementation | 8500
4.1.6 | Launch app v2 | 3 | 1 | 0 | 1500 | 500 | 2000 | Launch of the second version of the app
TOTAL cOSTS |  | 72 | 24 | 0 | 68700 | 14600 | 91500 | 0 | 147100
Contingency requirements (10%) | [8 empty] | 14710
Personnel cost requirements | [5 empty] | Note: Update cost categories to reflect actual project requirements
Rate | Name | Hours | Costs
50 | Internal Personnel | 200 | 10000
60 | External Personnel | 120 | 7200
TOTAL |  |  | 17200