## AHI WBS
|  | 1.0 AHI App Development Project |  |  | Level 1 Project level
1.1 Design Phase (30 Days) | 2.1 Development Phase (90 days) |  | 3.1 Test Phase (30 days) | 4.1 Launch and Improvement Phase (60 days) | Level 2 Phase level
1.1.1 Gain final design approval | 2.1.1 Develop initial prototype |  | 3.1.1 Test the final app prototype | 4.1.1 Launch the new app | Level 3 Work package level
1.1.2 Identify vendor to design and develop app | 2.1.2 Perform prototype beta test |  | 3.1.2 Begin full-scale development | 4.1.2 Monitor app performance
1.1.3 Solicit initial design feedback | 2.1.3 Solicit best test feedback |  | 3.1.3 Begin IT hiring | 4.1.3 Plan v2 upgrades
1.1.4 Define key app functionality requirements | 2.1.4 Update prototype based on feedback |  | 3.1.4 Gain customer acceptance | 4.1.4 Finalize new hires
1.1.5 Develop initial design | 2.1.5 Implement IT upgrades |  | 3.1.5 Approve the launch plan | 4.1.5 Implement app upgrades
1.1.6 Finalize vendor contract | 2.1.6 Develop an app launch plan |  | 3.1.6 Train Marketing personnels on new app | 4.1.6 Launch app v2
1.1.7 Update design based on feedback | 2.1.7 Gain prototype sign-off |  |  | 4.1.7 Document app issues
4.1.8 Complete the final project report